## SAMPLE - Release Burndown Chart
BURNDOWN CHART TEMPLATE
PROJECT TITLE |  |  |  |  | PROJECT MANAGER |  |  | DATE | VERSION | PROJECT ID
Project 1 |  |  |  |  | Al Raji |  |  | 2023-10-10 | 1.0 | PILOT-0628
| INITIAL ESTIMATE | WEEKS | [7 empty] | HOURS REMAINING
FEATURE |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Categories | 80 | 15 | 12 | 7 | 5 | 10 | 16 | 14 | 1 | 0
Synchronization | 80 | 12 | 8 | 5 | 7 | 9 | 6 | 11 | 12 | 10
Accounts | 80 | 9 | 8 | 7 | 6 | 5 | 7 | 9 | 11 | 18
Reminders | 80 | 13 | 9 | 7 | 5 | 4 | 6 | 8 | 12 | 16
|  | WEEKS 1: WEEKS | CHART ID
SETTING | START | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Planned Hours |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Actual Hours |  | 49 | 37 | 26 | 23 | 28 | 35 | 42 | 36
Remaining Effort | 320 | 271 | 234 | 208 | 185 | 157 | 122 | 80 | 44
Ideal Burndown | 320 | 280 | 240 | 200 | 160 | 120 | 80 | 40 | 0
PROJECT 1 BURNDOWN CHART